## Slide 1: IT Project Management (Introduction to Microsoft Project 1)
Instructor: Tran Vinh Khiem
March 1st, 2020
S3T
Smart Software System Team

## Slide 2
IT Project Management
“Being a Project Manager is like being an artist, you have the different colored process streams combining into a work of art.”
– Greg Cimmarrusti

## Slide 3: Learning Objectives
Understand the basic structure of Microsoft Project 2019
Know how to create new project, setting project options, create tasks and other necessary features.
Make a basic plan, timeline and grant chart.

## Slide 4: Set up
Follow this link: Install Project - Office Support (microsoft.com)
Use Microsoft account of UIT to activate Microsoft Project 2019

## Slide 5: Create MS Project
Open Microsoft Project  select Blank Project.

## Slide 6: Project Option
Open File  Options  Project Option.

## Slide 7: Schedule
Click on Schedule  Week starts on  Choose Monday.
Assign start time to 9:00 AM, end time to 6:00 PM, Days per month to 22.

## Slide 8: Currency
Click on Display  Currency  Choose VND.

## Slide 9: Task
Click on Task  Task Name  Add new tasks

## Slide 10: Indent Task
Choose all tasks below Learning Project Management
Task  Schedule  Select Indent task

## Slide 11: Indent Task

## Slide 12: Exercise 1
Make Learning Plan as below:

## Slide 13: Link the selected task
Task  Schedule  Link selected task (Crt + F2)

## Slide 14: View entire project
View  Zoom  Entire Project

## Slide 15: Set predecessors
Click on Predecessors

## Slide 16: Set predecessors
Task information  Predecessor  ID

## Slide 17: Task mode
Task mode  Manually or Automatic. Try to change as below:

## Slide 18: Task type
Double click on Task name  Task information  Advanced  Task Type

## Slide 19: Task dependencies
Finish-to-Start Dependencies (FS) : The predecessor must be finished before the successor start.
Start-to-Start Dependencies (SS): The successor task cannot start until the predecessor task starts

## Slide 20: Task dependencies
Finish-to-Finish Dependencies (FF) : The successor cannot finish until the predecessor task finish.
Start-to-Finish Dependencies (SF): The successor task cannot finish until the predecessor task starts
Predecessor
Successor

## Slide 21: Task dependencies
Finish-to-Finish Dependencies (FF) : The successor cannot finish until the predecessor task finish.
Start-to-Finish Dependencies (SF): The successor task cannot finish until the predecessor task starts
Predecessor
Successor

## Slide 22: Tracking progress
Select Tasks  On Schedule, choose 0, 25, 50, 75 or 100%

## Slide 23: Inactive task
Select Task Name  Task  Schedule  Inactive Task. Note : Task in progress cannot be Inactive.

## Slide 24: Holiday
Project  Change working time

## Slide 25: Holiday
Click on Detail  Nonworking or edit Working times, recurrence pattern,…

## Slide 26: Insert new column
Right click on any column  Select Insert Column

## Slide 27: Timeline
Double click on Task Name  Task Information  General  Display on Timeline

## Slide 28: Exercise 2
Create timeline likes this.

## Slide 29: Exercise 3

## Slide 30: Exercise 4

## Slide 31: Exercise 5

## Slide 32: Exercise 6

## Slide 33: Q & A
Thank you for attention
“Coming together is a beginning;
Keeping together is progress;
Working together is success.”
- HENRY FORD